## Tabelle1
Risk | Description | Prob. Of Occurrence | Damage | Mitigation Strategy | Person in Charge | Risk Factor
Project involves the use of technology that has not been used prior project |  | 10 | 6 | Learn the technology | everyone | 27
Team members lack of specialized skill required by the project |  | 9 | 5 | aquire specialized skills | everyone | 18
Inexperience project management |  | 9 | 4 | collect experience | David | 12
Inexperience team members |  | 9 | 4 | we are students | everyone | 30
Inadequate estimation of required resources |  | 7 | 5 | collect experience | David | 14
High level of technical complexity |  | 5 | 6 | break down complexity | Robin | 12
Project mile stone not clearly defined |  | 9 | 3 | planning mile stones | David | 60
Project involves the use of new technology |  | 9 | 2 | using things we know, watching tutorials and asking other groups for help | Tom | 14
Contiually changing requirements |  | 2 | 7 | working agile | Tom | 35
Ineffective communications |  | 2 | 7 | planed meetings | Tom | 45
Unclear system requirements |  | 4 | 3 | write requirements down and communicate | Robin | 12
Project progress not monitored closely enough |  | 3 | 4 | more excessive use of YouTrack | Robin | 36
Poor project planning |  | 3 | 4 | planning together better | Tom | 36