## Tabelle1
Risk | Prob. Of Occurrence | Damage | Mitigation Strategy | Person in Charge | Risk Factor
Project involves the use of technology that has not been used prior project | 10 | 6 | Learn the technology | everyone | 60
Team members lack of specialized skill required by the project | 9 | 5 | aquire specialized skills | everyone | 45
Inexperience project management | 9 | 4 | collect experience | David | 36
Inexperience team members | 9 | 4 | we are students | everyone | 36
Inadequate estimation of required resources | 7 | 5 | collect experience | David | 35
High level of technical complexity | 5 | 6 | break down complexity | Robin | 30
Project mile stone not clearly defined | 9 | 3 | planning mile stones | David | 27
Project involves the use of new technology | 9 | 2 | using things we know, watching tutorials and asking other groups for help | Tom | 18
Contiually changing requirements | 2 | 7 | working agile | Tom | 14
Ineffective communications | 2 | 7 | planed meetings | Tom | 14
Unclear system requirements | 4 | 3 | write requirements down and communicate | Robin | 12
Project progress not monitored closely enough | 3 | 4 | more excessive use of YouTrack | Robin | 12
Poor project planning | 3 | 4 | planning together better | Tom | 12